## Sheet1
Benzene Bots Timeline 2017			7-Jan	8-Jan	9-Jan	10-Jan	11-Jan	12-Jan	13-Jan	14-Jan	15-Jan	16-Jan	17-Jan	18-Jan	19-Jan	20-Jan	21-Jan	22-Jan	23-Jan	24-Jan	25-Jan	26-Jan	27-Jan	28-Jan	29-Jan	30-Jan	31-Jan	1-Feb	2-Feb	3-Feb	4-Feb	5-Feb	6-Feb	7-Feb	8-Feb	9-Feb	10-Feb	11-Feb	12-Feb	13-Feb	14-Feb	15-Feb	16-Feb	17-Feb	18-Feb	19-Feb	20-Feb	21-Feb

Kickoff event
Rules+Brainstorm
Drive design
Drive Finalized
Mechanism prototype
Build Drive
Design Mechs
Build Mechs
Driver Station
Finish Robo #1
Build Robo #2
Finish Robo#2
Code
Sensors/Camera
Auton
Practice+Tweaks